## Sheet1
Function	Quick test	In-progress by	Test written?	Test Run?	Tested by Production tester?	Comment
Hardware
Power-on	X	bunnie		X	X
3.3V regulator	X	bunnie		X	X
SWD	X	bunnie		X	X
Reset switch	X	bunnie		X
Reset-hold	X	bunnie		X
power LED	X	bunnie		X
power error LED		bunnie
program LED	FAIL	bunnie		X		Should flash during programming, but stays red
run LED	X	bunnie		X
A0-5 LED array	X	bunnie		X
RGB LED	X	bunnie
Reverse power		bunnie
TX overvoltage		bunnie
UART TX	X	bunnie
UART RX		bunnie
audio programming	X	bunnie
USB low speed
USB power
32kHz crystal		bunnie
A0-5 hi-Z performance	X	bunnie

OS firmware
fp casts			done
fp compares			done
fp mul div sub add			done
fp string		bunnie
fp cos sin tan sqrt			done
fp atan2 exp ln	FAIL		done			not implemented in OS?
snprintf integer		bunnie	done
snprintf float	FAIL					doesn't work
strncpy cpy cmp ncmp chr len		bunnie	done
atol
strtoul, strtol, etc.	FAIL					not implemented in OS?
ltoa, utoa, etc.	FAIL					not implemented in OS?
printf putchar getchar cangetchar
pinMode
analogReference
analogWrite	X
analogRead	X
digitalWrite	X
digitalRead	X
pinMode	X
Attach/detachInterrupt
Attach/detachFastinterrupt
tone/noTone
shiftOut/In
pulseIn/long
random/randomSeed
millis
micros
delay	X
delayMicroseconds	X
i2cTranscieve/SetupSlave
hookSoftPwm
getOSVersion
getHWVersion
createThread	X
suspendThread
exitThread
resumeThread
yieldThread
threadSleep/Until
setThreadName
setTimer/resetTimer
mutexInit/Lock/Trylock/Unlock
flashErase/flashWrite
doSudo
setSerialSpeed
hookSysTick
ledShow

Server firmware
WS2812B	X
eeprom (flasherase, flashwrite)
USB low speed
servo
map
lowByte, highByte
bitRead, bitWrite
bitSet, BitClear, bit