## Sheet1
Function	Quick test	In-progress by	Test written?	Test Run?	FW version	Tested by Production tester?	Comment
Hardware
Power-on	X	bunnie		X		X
3.3V regulator	X	bunnie		X		X
SWD	X	bunnie		X		X
Reset switch	X	bunnie		X
Reset-hold	X	bunnie		X
power LED	X	bunnie		X
power error LED		bunnie
program LED	FAIL	bunnie		X			Should flash during programming, but stays red
run LED	X	bunnie		X
A0-5 LED array	X	bunnie		X
RGB LED	X	bunnie
Reverse power		bunnie
TX overvoltage		bunnie
UART TX	X	bunnie
UART RX		bunnie
audio programming	X	bunnie
USB low speed
USB power
32kHz crystal		bunnie
A0-5 hi-Z performance	X	bunnie

OS firmware
fp casts			done	pass	0x105
fp compares			done	pass	0x105
fp mul div sub add			done	pass	0x105
fp cos sin tan sqrt			done	pass	0x105
fp atan2 exp ln			done	FAIL	0x105		not implemented in OS?
snprintf integer			done	pass	0x105
snprintf float			done	FAIL	0x105		doesn't work
strncpy cpy cmp ncmp chr len			done	pass	0x105
atol			done	pass	0x105
strtoul, strtol, etc.			done	FAIL	0x105		not implemented in OS?
ltoa, utoa, etc.			done	FAIL	0x105		not implemented in OS?
printf			done	pass	0x105
getchar cangetchar putchar			done	FAIL	0x105		not implemented in OS?
analogReference
analogWrite	x		done	pass	0x105
analogRead	x		done	FAIL	0x105		fails on A4, A5
digitalWrite	x		done	FAIL	0x105		fails on A0-A3 after analogWrite() to those pins
digitalRead	x		done	pass	0x105
pinMode	x		done	pass	0x105
Attach/detachInterrupt
Attach/detachFastinterrupt
tone/noTone
shiftOut/In
pulseIn/long
random/randomSeed
millis
micros
delay	X
delayMicroseconds	X
i2cTranscieve/SetupSlave
hookSoftPwm
getOSVersion			done	FAIL	0x105		not implemented in OS?
getHWVersion			done	FAIL	0x105		not implemented in OS?
createThread	x		done	pass	0x105
suspendThread
exitThread
resumeThread
yieldThread	x		done	pass	0x105
threadSleep/Until			done	FAIL	0x105		threadSleep is unstable for amount of time it sleeps
setThreadName
setTimer/resetTimer
mutexInit/Lock/Trylock/Unlock
flashErase/flashWrite
doSudo
setSerialSpeed
hookSysTick
ledShow			done	pass	0x105		use the neopixel sample program

Server firmware
WS2812B	FAIL		done	fail	0x105		unstable on firmware 0x105 – too many interrupts hooked?
serialEvent	FAIL						simply don't support on LTC?
eeprom (flasherase, flashwrite)
USB low speed
servo
map
lowByte, highByte
bitRead, bitWrite
bitSet, BitClear, bit