## Sheet1
Function	Quick test	In-progress by	Test written?	Test Run?	Tested by Production tester?	Comment
Hardware
Power-on	X	bunnie		X	X
3.3V regulator	X	bunnie		X	X
SWD	X	bunnie		X	X
Reset switch	X	bunnie		X
Reset-hold	X	bunnie		X
power LED	X	bunnie		X
power error LED		bunnie
program LED	FAIL	bunnie		X		Should flash during programming, but stays red
run LED	X	bunnie		X
A0-5 LED array	X	bunnie		X
RGB LED	X	bunnie
Reverse power		bunnie
TX overvoltage		bunnie
UART TX	X	bunnie
UART RX		bunnie
audio programming	X	bunnie
USB low speed
USB power
32kHz crystal		bunnie
A0-5 hi-Z performance	X	bunnie

OS firmware
fp casts			done	pass
fp compares			done	pass
fp mul div sub add			done	pass
fp cos sin tan sqrt			done	pass
fp atan2 exp ln	FAIL		done	FAIL		not implemented in OS?
snprintf integer			done	pass
snprintf float	FAIL		done	FAIL		doesn't work
strncpy cpy cmp ncmp chr len			done	pass
atol			done	pass
strtoul, strtol, etc.	FAIL		done	FAIL		not implemented in OS?
ltoa, utoa, etc.	FAIL		done	FAIL		not implemented in OS?
printf			done	pass
getchar cangetchar putchar	FAIL		done	FAIL		not implemented in OS?
pinMode
analogReference
analogWrite	X
analogRead	X
digitalWrite	X
digitalRead	X
pinMode	X
Attach/detachInterrupt
Attach/detachFastinterrupt
tone/noTone
shiftOut/In
pulseIn/long
random/randomSeed
millis
micros
delay	X
delayMicroseconds	X
i2cTranscieve/SetupSlave
hookSoftPwm
getOSVersion	FAIL		done	FAIL		not implemented in OS?
getHWVersion	FAIL		done	FAIL		not implemented in OS?
createThread	X
suspendThread
exitThread
resumeThread
yieldThread
threadSleep/Until
setThreadName
setTimer/resetTimer
mutexInit/Lock/Trylock/Unlock
flashErase/flashWrite
doSudo
setSerialSpeed
hookSysTick
ledShow

Server firmware
WS2812B	X
serialEvent	FAIL					simply don't support on LTC?
eeprom (flasherase, flashwrite)
USB low speed
servo
map
lowByte, highByte
bitRead, bitWrite
bitSet, BitClear, bit