## version 0x105
Function	Quick test	In-progress by	Test written?	Test result?	FW version	Tested by Production tester?	Comment
Hardware
Power-on	X			pass		X
3.3V regulator	X			pass		X
SWD	X			pass		X
Reset switch	X			pass
Reset-hold	X			pass
power LED	X			pass
power error LED		bunnie
program LED	FAIL	bunnie		FAIL	0x105		Should flash during programming, but stays red
run LED	X			pass	0x105
A0-5 LED array	X			pass	0x105
RGB LED	X			pass	0x105		basic test passes, but driver is unstable
RGB LED external drive				pass	0x015		includes test of current sourcing
Reverse power		bunnie
TX overvoltage		bunnie
UART TX	X			pass	0x105		tested at 9600 baud
UART RX		N/A		N/A			not testable
audio programming	X			pass	0x105		need to add multi-rate support
USB low speed
USB power
32kHz crystal		bunnie
A0-5 hi-Z performance	X			pass	0x105		test by setting A0-A5 to INPUT and touching pins

OS firmware
fp casts			done	pass	0x105
fp compares			done	pass	0x105
fp mul div sub add			done	pass	0x105
fp cos sin tan sqrt			done	pass	0x105
fp atan2 exp ln			done	FAIL	0x105		not implemented in OS?
snprintf integer			done	pass	0x105
snprintf float			done	FAIL	0x105		doesn't work
strncpy cpy cmp ncmp chr len			done	pass	0x105
atol			done	pass	0x105
strtoul, strtol, etc.			done	FAIL	0x105		not implemented in OS?
ltoa, utoa, etc.			done	FAIL	0x105		not implemented in OS?
printf			done	pass	0x105
getchar cangetchar putchar			done	FAIL	0x105		not implemented in OS?
analogReference		N/A					function is a no-op
ADC temperature sensor			done	pass	0x015		Nice-to-have but not essential
analogWrite	x		done	pass	0x105
analogRead	x		done	FAIL	0x105		fails on A4, A5
analogReadResolution				FAIL	0x105		required for Arduino compliance
digitalWrite	x		done	FAIL	0x105		fails on A0-A3 after analogWrite() to those pins
digitalRead	x		done	pass	0x105
pinMode	x		done	pass	0x105
Attach/detachInterrupt			done	FAIL	0x015		lacks digitalPinToInterrupt() API, recommended by Arduino reference
Attach/detachFastinterrupt		N/A					not part of official arduino API
tone/noTone			done	FAIL	0x105		doesn't seem to work in compound situations / tone too low by factor of 2 in simple situations
shiftOut/In			done	FAIL	0x105		getting all 0's, need to investigate why.
pulseIn/long			done	FAIL	0x105		doesn't work for LOW, or on high port numbers
random/randomSeed			done	FAIL	0x105		random generates negative numbers
millis			done	pass	0x105		drift compared against a 1-minute run
micros			done	pass	0x105		OSC0_CR confirmed to have a value of 0x0C, and IREFS is 0
delay	X		done	pass	0x105
delayMicroseconds	X		done	pass	0x105
i2cTranscieve/SetupSlave		if this is broken, we can just patch server-side, yes?
hookSoftPwm
getOSVersion			done	FAIL	0x105		not implemented in OS?
getHWVersion			done	FAIL	0x105		not implemented in OS?
createThread	x		done	pass	0x105
suspendThread
exitThread
resumeThread
yieldThread	x		done	pass	0x105
threadSleep/Until			done	FAIL	0x105		threadSleep is unstable for amount of time it sleeps
setThreadName
setTimer/resetTimer
mutexInit/Lock/Trylock/Unlock
flashErase/flashWrite			done	FAIL	0x105		API doesn't seem to work?? data always reads back as 0xffffffff
doSudo
setSerialSpeed
hookSysTick
ledShow			done	pass	0x105		use the neopixel sample program

Server firmware
WS2812B	FAIL		done	pass	0x105
serialEvent	FAIL						simply don't support on LTC?
eeprom (flasherase, flashwrite)
USB low speed
servo
map
lowByte, highByte
bitRead, bitWrite
bitSet, BitClear, bit
string concatenation				fail	0x105